## Issues Log
Open Geospatial Metadata Element Set - Issues Log

Metadata Field	Issue	Notes	Next Steps	Status
Content Type	Which fields should be added to the existing content type controlled vocabulary for the open data portal (Dataset, API, Supporting Document, and App)	Web Service' was suggeted, are there any others?	Group to discuss	In progress
Content Type	How will this element be mapped from the HNAP to OGDMES		Group to discuss	In progress
Format	Which fields should be added to the existing format controlled vocabulary for the open data portal?	Arthur and Cindy propose : ESRI Map Service and ESRI Feature Service / Are these elements bilingual? / See mapping in tab 2	Group to discuss	In progress
Language	How we describe bilingual resources ?	It was proposed to leave this blank, and then assume those bilingual, but this is not a good appraoch, because users could just forget to enter the filed..and there will be a possibility of biligual records that are not eng / fra	Group to discuss	In progress
Metadata Identifier	We need to determine how this will be generated	Note from Mark Shaw / "XML of Metadata / - Rather than transferring and storing a physical file, the External FGP catalogue can generate this on request in a few mechanisms: / o A CSW request to get the xml can be requested using a GetRecordByID call GeoNetworkServer/csw?service=CSW&version=2.0.2&request=GetRecordById&outputSchema=csw:IsoRecord&id=698ea2e7-8025-481b-a011-7ff6232939aa / o Or by using the Geonetwork API http://server/geonetwork/srv/eng/xml.metadata.get?uuid=698ea2e7-8025-481b-a011-7ff6232939aa / - Both of these options will return the full standalone xml record from the catalogue that a user can view and save. / Preferred option is 1 via CSW. The FGP external server name is unknown"	Group to discuss	In progress
RAMP	Which elements are required to support the RAMP functionality	Note from Mark Shaw "The only thing needed to support calling RAMP is the short key. There are a few options for how the GeoNetwork can share this with the open portal, but from a metadata perspective, it does not need to be stored as part of this. Its really a technical implementation that doesn’t belong as part of NAP. We just need to be able to support matching a UUID to a small key. The rest of the information is handled by the external FGP catalogue and external RCS client". / Is there a potential for collisions between records (i.e. if we truncate the i.d. and mutliple records have the same characters)..	Group to discuss	In progress
Aggregation Information	Is there a need to add additional 'Aggregation Information' fields to support this? Currently we have captured : associationType and aggregateDatasetIdentifer. Is there a need to add aggregateDatasetName, alternateTitle, etc.	This element is to point to another metadata records that is related to the current record. So all you (and NAP) requires are the two elements listed : associationType and aggregateDatasetIdentifier / However, we will need to determine how this id generates the URL to the accompanied record	Group to discuss
Facets	Which elements should be provided as facets on the FGP Search Page	See mock-up	Group to discuss, and provide feedback by March 5	In progress
Metadata Record View	Which elements should be represented on the metadata record	See mock-up	Group to discuss, and provide feedback by March 5	In progress

## File Format Mapping
File Format Comparison

HNAP v2.2	ODMES Format type
AI	AI
AMF	AMF
Application	Application
ASCII Grid	ASCII Grid
	BMP
CDED ASCII	CDED ASCII
CDR	CDR
CSV	CSV
DOC	DOC
dxf	dxf
E00	E00
ECW	ECW
EDI	EDI
EMF	EMF
EPS	EPS
ESRI REST
EXE	EXE
FGDB / GDB	FGDB / GDB
Flat raster binary	Flat raster binary
GeoPDF	GeoPDF
GeoRSS	GeoRSS
	GeoTIF
GIF	GIF
GML	GML
HDF	HDF
HTML	HTML
IATI	IATI
JPEG 2000	JPEG 2000
JPG	JPG
JSON	JSON
JSON Lines	JSON Lines
KML / KMZ	KML / KMZ
NetCDF	NetCDF
ODP	ODP
ODS	ODS
ODT	ODT
Other	Other
PDF	PDF
PNG	PNG
PPT	PPT
RDF	RDF
RDFa	RDFa
RSS	RSS
RTF	RTF
SAR / CCT	SAR / CCT
SAV	SAV
SEGY	SEGY
SHP	SHP
SQL	SQL
	SVG
TIFF World File	TIFF
TIFF	TIFF World File
TXT	TXT
WFS	WFS
WMS	WMS
WMTS	WMTS
XLS	XLS
XLSM	XLSM
XML	XML
Zip	Zip